## Home
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Full HTML CSS | 2025-06-15 | 2025-06-15 | 100% | Nghiêm
Logo |  |  | 100% | Nghiêm
Navbar |  |  | 100% | Nghiêm
Submenu |  |  | 100% | Nghiêm
Search form |  |  | 100% | Nghiêm
Login popup |  |  | 100% | Nghiêm
Feature render product | 2025-06-19 | 2025-06-19 | 100% | Nghiêm
Feature add to cart | 2025-06-20 | 2025-06-20 | 100% | Nghiêm
Feature Save product to localStorage | 2025-06-21 | 2025-06-21 | 100% | Nghiêm
Feature pay for your order to clear cart | 2025-06-21 | 2025-06-21 | 100% | Nghiêm
Feature remove product from cart | 2025-06-21 | 2025-06-21 | 100% | Nghiêm
Feature down & up product in cart | 2025-06-21 | 2025-06-21 | 100% | Nghiêm
Feature calculate the total price of all products | 2025-06-21 | 2025-06-22 | 100% | Nghiêm

## Admin
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Full HTML CSS | 2025-06-15 | 2025-06-15 | 100% | Nghiêm
Logo |  |  | 50% | Nghiêm |  |  | 50% | Nhật Trường
Navbar | 2019-05-23 | 2019-07-01 | 90% | Nghiêm |  |  | 90% | Nhật Trường
Submenu | 2019-05-23 | 2019-05-31 | 100% | Nghiêm |  |  | 100% | Nhật Trường
Search form | 2019-06-20 | 2019-06-28 | 90% | Nghiêm |  |  | 90% | Nhật Trường
Login popup | 2019-06-25 | 2019-07-01 | 80% | Nghiêm |  |  | 80% | Nhật Trường
Feature add | 2025-06-15 | 2025-06-15 | 100% | Nghiêm
Feature edit | 2025-06-15 | 2025-06-15 | 100% | Nghiêm
Feature delete | 2025-06-15 | 2025-06-15 | 100% | Nghiêm
Feature validation | 2025-06-18 | 2025-06-18 | 100% | Nghiêm
Feature find product | 2025-06-19 | 2025-06-19 | 100% | Nghiêm
Feature filter product | 2025-06-19 | 2025-06-20 | 100% | Nghiêm